## Product Backlog
FRAUD DETECTION SYSTEM — Product Backlog v1.0
Project | Fraud Detection System (FDS) | Client | GlobalBank | Sprint | Sprint 1 | Last Updated | 22 May 2026 | Total Stories | 25 | Done | 8
Story ID | Epic | Type | Summary | User Story | Acceptance Criteria | Priority | Story Points | Status | Sprint | Assignee | REQ-ID | Labels
FDS-01 | Authentication | Story | Login as ops analyst | As an ops analyst, I want to log in with my credentials so that I can access the fraud review dashboard. | Given valid username and password, When POST /auth/login, Then 200 with JWT token + user object Given invalid credentials, When POST /auth/login, Then 401 with { error: 'Invalid credentials' } Given missing body fields, When POST /auth/login, Then 400 | Must Have | 3 | Done | Sprint 1 | Dev Team | REQ-004 | auth,backend
FDS-02 | Authentication | Story | JWT protects all routes | As a developer, I want all non-auth routes protected by JWT middleware so that unauthorised users cannot access any data. | Given no Authorization header, When any protected endpoint is called, Then 401 Given expired JWT, When any protected endpoint is called, Then 401 Given valid JWT, When any protected endpoint is called, Then request proceeds normally | Must Have | 2 | Done | Sprint 1 | Dev Team | REQ-004 | auth,backend,security
FDS-03 | Authentication | Task | Auth middleware unit tests | As a developer, I want unit tests for the auth middleware so that token validation logic is provably correct. | Given valid token, authMiddleware calls next() Given missing/invalid token, authMiddleware calls next with 401 error Test coverage for auth.js >= 90% | Must Have | 2 | Done | Sprint 1 | Dev Team | REQ-004 | testing,auth
FDS-04 | Transactions | Story | View paginated transaction list | As an ops analyst, I want to view a paginated list of transactions so that I can efficiently review them one page at a time. | Given authenticated user, When GET /transactions, Then 200 with array of ≤50 transactions ordered by date DESC Given page=2, When GET /transactions?page=2, Then correct offset applied Given no token, When GET /transactions, Then 401 Transaction object includes: id, amount, date, merchant, account_id, status | Must Have | 5 | In Progress | Sprint 1 | Dev Team | REQ-001 | transactions,backend
FDS-05 | Transactions | Story | Mark transaction as fraud | As an ops analyst, I want to mark a transaction as fraud so that it is flagged for further investigation and the decision is recorded. | Given authenticated user, When PATCH /transactions/:id/status with { status: 'fraud' }, Then 200 with updated transaction Given marking as fraud, Then one audit_log entry is written with new_status, marked_by, timestamp Given invalid status value (e.g. 'FRAUD' uppercase), Then 400 Given non-existent transaction ID, Then 404 | Must Have | 5 | In Progress | Sprint 1 | Dev Team | REQ-002 | transactions,backend,audit
FDS-06 | Transactions | Story | Mark transaction as legitimate | As an ops analyst, I want to mark a transaction as legitimate so that it is cleared from review and the decision is recorded. | Given authenticated user, When PATCH /transactions/:id/status with { status: 'legitimate' }, Then 200 with updated transaction Given marking as legitimate, Then audit_log entry written Given null status in body, Then 400 Given empty body, Then 400 | Must Have | 3 | To Do | Sprint 1 | Dev Team | REQ-002 | transactions,backend
FDS-07 | Transactions | Story | Transaction status badge display | As an ops analyst, I want each transaction to show a clear status badge so that I can see at a glance which transactions still need review. | Given status = 'unmarked', badge is grey ⚪ Given status = 'fraud', badge is red 🔴 Given status = 'legitimate', badge is green 🟢 Badge updates immediately on mark action (optimistic UI) | Must Have | 3 | To Do | Sprint 1 | Dev Team | REQ-001 | ui,frontend
FDS-08 | Transactions | Bug | Fix: transaction list not ordered newest first | As an ops analyst, I want to always see the most recent transactions first so that I review the latest activity immediately on load. | Given GET /transactions, response array is ordered by date DESC Most recent transaction appears at index 0 Ordering is applied at the DB query level (not client-side sort) | Must Have | 1 | To Do | Sprint 1 | Dev Team | REQ-001 | bug,transactions,backend
FDS-09 | Transactions | Task | Transaction service unit tests | As a developer, I want unit tests for transactionService so that all business logic is provably correct without HTTP. | Tests for getList(): pagination, ordering, max 50 limit Tests for updateStatus(): valid/invalid status, audit log write Coverage for transactionService.js >= 80% Tests run without HTTP (direct service import) | Must Have | 3 | To Do | Sprint 2 | Dev Team | REQ-001 | testing,transactions
FDS-10 | Audit Trail | Story | View transaction audit trail | As an ops analyst, I want to see the full audit trail for any transaction so that I can review the history of decisions made on it. | Given authenticated user, When GET /transactions/:id/history, Then 200 with array of audit entries ordered newest first Audit entry includes: id, transaction_id, new_status, marked_by, timestamp Given no audit history, Then 200 with empty array Given non-existent transaction ID, Then 404 | Must Have | 3 | To Do | Sprint 1 | Dev Team | REQ-003 | audit,backend
FDS-11 | Audit Trail | Story | Audit entry written on every status change | As a compliance officer, I want every status change to be written to the audit log automatically so that no decision goes unrecorded. | Every PATCH /transactions/:id/status creates exactly one audit_log row Audit row includes: transaction_id, new_status, marked_by (from JWT), timestamp (server time) Audit writes are transactional — if the status update fails, no audit entry is written Audit entries are immutable — no DELETE or UPDATE on audit_log rows | Must Have | 3 | To Do | Sprint 1 | Dev Team | REQ-003 | audit,backend,compliance
FDS-12 | Audit Trail | Story | Collapsible audit trail in UI | As an ops analyst, I want to expand an audit trail panel for any transaction without leaving the main list so that I can review history efficiently. | Clicking a transaction row expands a collapsible audit panel below it Panel fetches GET /transactions/:id/history on expand (not on page load) Each entry shows: analyst name, new status, timestamp formatted as 'DD MMM YYYY HH:MM' Panel collapses when clicked again | Should Have | 3 | To Do | Sprint 2 | Dev Team | REQ-003 | audit,ui,frontend
FDS-13 | Audit Trail | Task | Audit log DB migration | As a developer, I want the audit_log table created by a migration script so that DB setup is repeatable and version-controlled. | Migration creates table: audit_log (id TEXT PK, transaction_id TEXT, new_status TEXT, marked_by TEXT, timestamp TEXT) Migration is idempotent (safe to run twice) Migration script lives in db/migrations/ | Must Have | 1 | Done | Sprint 1 | Dev Team | REQ-003 | database,setup
FDS-14 | Security | Story | Parameterised DB queries (SQL injection prevention) | As a developer, I want all database queries to use parameterised statements so that SQL injection attacks are impossible. | All DB queries in db/ layer use ? placeholders, never string interpolation SonarQube scan shows zero SQL injection warnings Code review checklist includes: 'All DB queries parameterised?' | Must Have | 2 | Done | Sprint 1 | Dev Team | REQ-004 | security,backend
FDS-15 | Security | Story | Status enum validation on PATCH endpoint | As a developer, I want PATCH /transactions/:id/status to reject any status value not in the approved list so that invalid data cannot enter the system. | Given status = 'fraud', Then 200 — accepted Given status = 'legitimate', Then 200 — accepted Given status = 'FRAUD' (wrong case), Then 400 Given status = 'deleted', Then 400 Given status = null, Then 400 Given status = '' (empty string), Then 400 | Must Have | 2 | To Do | Sprint 1 | Dev Team | REQ-002 | security,validation,backend
FDS-16 | Security | Story | No stack traces in error responses | As a developer, I want error responses to return clean JSON without stack traces so that internal implementation details are not exposed to clients. | Given any unhandled error, API returns { error: 'Internal server error' } with 500 Stack trace is logged server-side but never returned in response body SonarQube scan shows zero sensitive data exposure warnings | Must Have | 1 | To Do | Sprint 1 | Dev Team | REQ-004 | security,backend
FDS-17 | Security | Bug | Fix: SonarQube Critical — hardcoded JWT secret | As a developer, I want the JWT secret loaded from environment variables so that it is not exposed in source code. | JWT_SECRET read from process.env.JWT_SECRET .env file added to .gitignore SonarQube scan shows zero hardcoded credential warnings App fails to start with clear error if JWT_SECRET not set | Must Have | 1 | To Do | Sprint 1 | Dev Team | REQ-004 | bug,security,critical
FDS-18 | User Interface | Story | Transaction table renders on load | As an ops analyst, I want the transaction list to load automatically when I open the app so that I can start reviewing immediately. | On page load, GET /transactions is called automatically Table renders with columns: Date, Merchant, Account ID, Amount, Status Loading spinner shown while fetching Empty state message shown if no transactions returned | Must Have | 3 | To Do | Sprint 1 | Dev Team | REQ-001 | ui,frontend
FDS-19 | User Interface | Story | Fraud / Legitimate action buttons per row | As an ops analyst, I want Fraud and Legitimate buttons on each transaction row so that I can mark decisions without navigating away from the list. | Each row has two buttons: 'Mark Fraud' and 'Mark Legitimate' Clicking a button triggers PATCH /transactions/:id/status Optimistic UI: status badge updates immediately before response On API error: badge reverts and error toast is shown Buttons disabled while request is in-flight | Must Have | 5 | To Do | Sprint 1 | Dev Team | REQ-002 | ui,frontend
FDS-20 | User Interface | Story | UI Design — styling sprint | As an ops analyst, I want the interface to be visually clear and density-appropriate so that I can review many transactions quickly without eye strain. | Max 3 brand colours used Status badges are visually distinct at a glance (colour + icon) Table row height allows 20+ rows visible without scrolling on a 1080p monitor UI passes basic accessibility check (colour contrast >= 4.5:1) | Should Have | 3 | To Do | Sprint 2 | Dev Team | REQ-001 | ui,design,frontend
FDS-21 | Setup & Config | Task | Project scaffold — folder structure | As a developer, I want the agreed folder structure committed to main so that all developers follow the same architecture from Day 1. | Folders created: routes/, controllers/, services/, db/, middleware/, views/, agents/, tests/, spec/ Each folder has an index.js or .gitkeep README.md documents the layering rule: routes→controllers→services→db | Must Have | 1 | Done | Sprint 1 | Dev Team | REQ-004 | setup,architecture
FDS-22 | Setup & Config | Task | SQLite DB migrations — transactions table | As a developer, I want the transactions table created by a migration script so that DB setup is repeatable. | Migration creates: transactions (id TEXT PK, amount REAL, date TEXT, merchant TEXT, account_id TEXT, status TEXT DEFAULT 'unmarked') Migration is idempotent Seed script inserts 20 test transactions with mixed statuses | Must Have | 1 | Done | Sprint 1 | Dev Team | REQ-001 | database,setup
FDS-23 | Setup & Config | Task | Seed data — 20 test transactions | As a developer, I want 20 realistic seed transactions so that the app can be demoed without manual data entry. | 20 transactions with: realistic merchant names, varied amounts ($12–$4200), mixed statuses (unmarked/fraud/legitimate), dates spanning last 30 days Seed script: npm run seed Seed is safe to run multiple times (clears and re-inserts) | Must Have | 1 | Done | Sprint 1 | Dev Team | REQ-001 | setup,data
FDS-24 | Setup & Config | Task | GitHub Actions CI pipeline | As a developer, I want a CI pipeline that runs tests on every PR so that broken code cannot be merged to main. | GitHub Actions workflow: triggers on PR to main Runs: npm install → npm test Fails build if any test fails Fails build if coverage drops below 70% | Must Have | 2 | To Do | Sprint 2 | Dev Team | REQ-004 | ci,devops,testing
FDS-25 | Setup & Config | Story | Operating Model documentation | As a new team member, I want a complete Operating Model document so that I can run and maintain the system without asking the original developers. | Sections: Pipeline Overview, Agent Config Guide, Environment Setup, Day-by-Day Run Guide, Troubleshooting (10 most common failures), Version History Environment setup steps verified on a fresh machine All agent system prompts documented with example inputs/outputs | Must Have | 5 | To Do | Sprint 2 | Dev Team | REQ-004 | documentation,delivery

## Sprint Board
FRAUD DETECTION SYSTEM — Sprint Board
Epic / Story ID | To Do | In Progress | Done | Blocked
EPIC: AUTHENTICATION
[FDS-01] Login as ops analyst REQ-004 · 3 pts · Must Have
[FDS-02] JWT protects all routes REQ-004 · 2 pts · Must Have
[FDS-03] Auth middleware unit tests REQ-004 · 2 pts · Must Have
EPIC: TRANSACTIONS
[FDS-04] View paginated transaction list REQ-001 · 5 pts · Must Have
[FDS-05] Mark transaction as fraud REQ-002 · 5 pts · Must Have
[FDS-06] Mark transaction as legitimate REQ-002 · 3 pts · Must Have
[FDS-07] Transaction status badge display REQ-001 · 3 pts · Must Have
[FDS-08] Fix: transaction list not ordered newest first REQ-001 · 1 pts · Must Have
[FDS-09] Transaction service unit tests REQ-001 · 3 pts · Must Have
EPIC: AUDIT TRAIL
[FDS-10] View transaction audit trail REQ-003 · 3 pts · Must Have
[FDS-11] Audit entry written on every status change REQ-003 · 3 pts · Must Have
[FDS-12] Collapsible audit trail in UI REQ-003 · 3 pts · Should Have
[FDS-13] Audit log DB migration REQ-003 · 1 pts · Must Have
EPIC: SECURITY
[FDS-14] Parameterised DB queries (SQL injection prevention) REQ-004 · 2 pts · Must Have
[FDS-15] Status enum validation on PATCH endpoint REQ-002 · 2 pts · Must Have
[FDS-16] No stack traces in error responses REQ-004 · 1 pts · Must Have
[FDS-17] Fix: SonarQube Critical — hardcoded JWT secret REQ-004 · 1 pts · Must Have
EPIC: USER INTERFACE
[FDS-18] Transaction table renders on load REQ-001 · 3 pts · Must Have
[FDS-19] Fraud / Legitimate action buttons per row REQ-002 · 5 pts · Must Have
[FDS-20] UI Design — styling sprint REQ-001 · 3 pts · Should Have
EPIC: SETUP & CONFIG
[FDS-21] Project scaffold — folder structure REQ-004 · 1 pts · Must Have
[FDS-22] SQLite DB migrations — transactions table REQ-001 · 1 pts · Must Have
[FDS-23] Seed data — 20 test transactions REQ-001 · 1 pts · Must Have
[FDS-24] GitHub Actions CI pipeline REQ-004 · 2 pts · Must Have
[FDS-25] Operating Model documentation REQ-004 · 5 pts · Must Have
SPRINT TOTALS | 15 stories | 2 stories | 8 stories

## Epic Summary
FRAUD DETECTION SYSTEM — Epic Summary
Epic | Colour | Stories | Done | In Progress | To Do | Story Points
Authentication | AUTH | 3 | 3 | 0 | 0 | 7
Transactions | TXN | 6 | 0 | 2 | 4 | 20
Audit Trail | AUDIT | 4 | 1 | 0 | 3 | 10
Security | SEC | 4 | 1 | 0 | 3 | 6
User Interface | UI | 3 | 0 | 0 | 3 | 11
Setup & Config | SETUP | 5 | 3 | 0 | 2 | 10
TOTAL |  | 25 | 8 | 2 | 15 | 64

## Req Traceability
FRAUD DETECTION SYSTEM — Requirements Traceability Matrix
REQ-ID | Title | Priority | Description | Covered By (Stories) | Status | Test Cases
REQ-001 | View transaction list | Must Have | Authenticated ops analysts can view a paginated list of transactions, max 50 per page, ordered newest first. | FDS-04, FDS-07, FDS-08, FDS-09, FDS-18, FDS-22, FDS-23 | In Progress | TC-001+
REQ-002 | Mark transaction status | Must Have | Analysts can mark any transaction as fraud or legitimate. Every status change writes one audit log entry. | FDS-05, FDS-06, FDS-07, FDS-15, FDS-19 | In Progress | TC-002+
REQ-003 | Audit trail | Must Have | Every status change is recorded. Analysts can view full history of decisions for any transaction. | FDS-10, FDS-11, FDS-12, FDS-13 | In Progress | TC-003+
REQ-004 | Authentication & security | Must Have | All routes protected by JWT. No hardcoded secrets. Parameterised DB queries. No stack traces in responses. | FDS-01, FDS-02, FDS-03, FDS-14, FDS-15, FDS-16, FDS-17, FDS-21, FDS-24, FDS-25 | In Progress | TC-004+